NORTHSTAR FINANCIAL SERVICES

Risk Management System

NS-AI-001 CreditScore Pro — EU AI Act Article 9

| Document Reference | NS-RMS-AI-001 |
| --- | --- |
| System | NS-AI-001 CreditScore Pro |
| Regulatory Basis | EU AI Act Article 9 — Risk Management System |
| Risk Tier | High Risk — Annex III Category 5(b) |
| Document Owner | Chief Risk Officer |
| Review Cycle | Annual — or upon material system change |

# 1. Purpose and Scope

This document records NorthStar's risk management system for CreditScore Pro as required by EU AI Act Article 9. Article 9 does not ask for a risk register — it asks for a system. A continuous, documented process that identifies, evaluates, mitigates, and monitors risks throughout the entire lifecycle of the AI system. CreditScore Pro has been in production since March 2022. A formal Article 9 risk management system did not exist before the Q1 2026 governance review. This document initiates that system and is honest about what existed before it.

# 2. Risk Identification

## 2.1 Methodology

Risk identification was conducted in January and February 2026 by the AI Governance Programme Office with the Head of Credit Risk and ML Engineering Lead. Three inputs were used: structured review of system design and operational data since March 2022, analysis of customer complaint patterns, and systematic Article 9-15 gap assessment.

## 2.2 Identified Risks — CreditScore Pro

| ID | Category | Description | Likelihood | Impact | Score |
| --- | --- | --- | --- | --- | --- |
| NS-RISK-001 | Bias | Postcode encoding ethnicity and socioeconomic status — discriminatory credit decisions for protected groups | 4 — Likely | 5 — Critical | 20/25 |
| NS-RISK-002 | Transparency | SHAP not deployed to Article 13 standard — declined applicants cannot receive compliant explanation | 4 — Likely | 4 — High | 16/25 |
| NS-RISK-007 | Model Drift | Training data ends 2021 — post-pandemic economic conditions not represented | 3 — Possible | 4 — High | 12/25 |
| NS-RISK-010 | Human Oversight | Override rate falling from 1.2% to 0.7% — automation bias undermining Article 14 | 4 — Likely | 3 — Medium | 12/25 |
| NS-RISK-011 | Data Quality | Thin-file applicants receiving lower confidence scores — disproportionate effect on young applicants and recent immigrants | 3 — Possible | 3 — Medium | 9/25 |

# 3. Risk Evaluation and Appetite

NorthStar's risk appetite for AI bias and fairness is zero. Any confirmed discriminatory outcome against a protected group is unacceptable regardless of operational benefit. This drives the Critical classification of NS-RISK-001 and its position as the highest priority remediation item in the portfolio.

For operational risks — NorthStar uses a defined threshold framework. Risks within threshold are monitored. Risks breaching threshold trigger mandatory review and potential system suspension.

## 3.1 Residual Risk — Post Controls

| Risk | Controls in Place | Control Effectiveness | Residual Rating |
| --- | --- | --- | --- |
| NS-RISK-001 | Bureau weighting. Loan officer override. | LOW — controls do not address root cause. No audit has confirmed or excluded discriminatory outcomes. | CRITICAL until bias audit complete |
| NS-RISK-002 | SHAP values generated and logged. | PARTIAL — SHAP exists technically but not customer-facing. | HIGH — Article 13 non-compliance remains |
| NS-RISK-007 | Monthly drift monitoring. Thresholds defined. | MODERATE — monitoring in place, no breach yet. | MEDIUM — monitor monthly |
| NS-RISK-010 | Loan officer review required before every decision. | LOW — review nominal not substantive given declining override rate. | HIGH — genuine oversight not exercised |

# 4. Mitigation Actions

| Risk | Action | Detail | Owner | Deadline |
| --- | --- | --- | --- | --- |
| NS-RISK-001 | Independent bias audit | External auditor assesses outcomes by gender, ethnicity, age. Postcode feature review included. | Head of Credit Risk | 30 Apr 2026 |
| NS-RISK-002 | SHAP documentation programme | Document methodology to Art. 13 standard. Design customer explanation process. Train loan officers. | Head of Credit Risk | 15 May 2026 |
| NS-RISK-007 | Retraining threshold definition | Define drift thresholds triggering mandatory retraining. Document governance approval process. | ML Engineering | 30 May 2026 |
| NS-RISK-010 | Loan officer training | Mandatory genuine oversight training. Override rate floor of 0.8% defined — sustained rates below trigger team review. | Head of Credit Risk | 30 May 2026 |

# 5. Ongoing Monitoring

- Daily — ML Engineering reviews performance metrics. Anomalies flagged same day to Head of Credit Risk.

- Weekly — Rejection rate analysis by postcode segment. Unusual patterns escalated to AI Risk Committee.

- Monthly — Full performance report to AI Risk Committee. Override rate trend reviewed.

- Quarterly — Bias indicator review. Demographic outcome analysis once audit baseline established.

- Annually — Full risk identification repeated. Register updated. Residual risk reassessed. This document reviewed and reissued.

Next scheduled review: April 2027. Document owner: Chief Risk Officer.