## Dashboard
NorthStar Financial Services — Policy Implementation Roadmap
90-Day AI Governance Remediation Programme ¦ April 2026 — June 2026 ¦ Version 1.0
Document Reference: NS-ROAD-AI-001 ¦ Owner: Chief Risk Officer ¦ Status: Active
Programme Summary
Phase 1 Days 1–30 |  |  | Phase 2 Days 31–60 |  | Phase 3 Days 61–90
Immediate Actions |  |  | Core Governance |  | Embedding
4 Critical actions 2 High actions |  |  | 5 Critical actions 2 High actions |  | 3 Medium actions 2 Monitor reviews
Priority Legend
CRITICAL Immediate legal exposure — must act now |  | HIGH Material risk — act within 30 days |  | MEDIUM Compliance gap — act within 60 days |  | MONITOR Adequate — maintain annual review
Portfolio Risk Summary — As at April 2026
System | Risk Tier | Maturity Score | Priority | Phase 1 Action | Phase 2 Action | Phase 3 Action
NS-AI-001 CreditScore Pro | High Risk | 1.75 | CRITICAL | SHAP documentation | Conformity assessment | Annual bias audit
NS-AI-002 FraudGuard 360 | Limited Risk | 3.0 | MEDIUM | — | Vendor contract update | Annual review
NS-AI-003 TalentMatch AI | High Risk | 1.0 | CRITICAL | Human override + Bias audit | Conformity assessment | Ongoing monitoring
NS-AI-004 SupportBot Aria | Limited Risk | 3.0 | MEDIUM | Mobile disclosure | — | Annual review
NS-AI-005 MarketSense | Minimal Risk | 3.0 | MONITOR | — | — | Annual review
NS-AI-006 DocIntel Underwriting | High Risk (pilot) | 1.0 | HIGH | Governance gate review | Conformity assessment gate | Production decision
NS-AI-007 RegulatoryRadar | Minimal Risk | 3.0 | MONITOR | — | — | Annual review

## Phase 1 — Days 1-30
Phase 1 — Immediate Actions (Days 1–30) NorthStar Financial Services — AI Governance Remediation Programme
These actions address immediate legal exposure under EU AI Act. All must be initiated on Day 1.
Ref | Action | System | Owner | Start Date | Deadline | EU AI Act Basis | Success Criteria
NS-ACT-001 | Implement mandatory human override for ALL TalentMatch AI shortlisting decisions. No candidate may be rejected based solely on AI output until conformity assessment is complete. | NS-AI-003 TalentMatch AI | HR Director | 1 Apr 2026 | 1 Apr 2026 (Immediate) | Article 14 — Human Oversight | Written confirmation from HR Director that manual review process is live. Override procedure documented and communicated to all HR staff.
NS-ACT-002 | Commission independent bias audit for TalentMatch AI covering gender, ethnicity, and age groups. Engage external auditor with NLP bias assessment capability. | NS-AI-003 TalentMatch AI | HR Director + ML Engineering | 1 Apr 2026 | 30 Apr 2026 | Article 10 — Data Governance | Bias audit report received. Results presented to AI Risk Committee. Remediation plan agreed if bias identified.
NS-ACT-003 | Document SHAP explainability tooling for CreditScore Pro to Article 13 standard. Produce technical explainability document covering: methodology, output format, limitation acknowledgment, deployer guidance. | NS-AI-001 CreditScore Pro | Head of Credit Risk + ML Engineering | 1 Apr 2026 | 15 May 2026 | Article 13 — Transparency | Technical explainability document completed and reviewed by Legal. SHAP output validated against Article 13 requirements.
NS-ACT-004 | Implement AI disclosure banner on SupportBot Aria mobile app channel. Disclosure must be clear, prominent, and displayed before the first AI interaction in every session. | NS-AI-004 SupportBot Aria | Head of Customer Experience + DialogueTech | 1 Apr 2026 | 30 Apr 2026 | Article 52(1) — AI Disclosure | Disclosure live on mobile channel. Screenshot evidence retained. Legal sign-off obtained.
NS-ACT-005 | Establish AI Risk Committee. Confirm membership, quorum rules, decision rights, and meeting cadence. Hold inaugural meeting. Agree Q2 agenda including conformity assessment approvals. | All systems | Chief Risk Officer | 1 Apr 2026 | 15 Apr 2026 | NIST AI RMF — GOVERN | AI Risk Committee constituted. Terms of Reference signed. Inaugural meeting minutes produced.
NS-ACT-006 | Deliver AI Governance Foundations training to all system owners. Cover: EU AI Act obligations, NIST AI RMF, incident escalation, system owner responsibilities under Operating Model. | All systems | Chief Risk Officer | 1 Apr 2026 | 30 Apr 2026 | NS-POL-AI-001 Section 12 | All system owners confirm completion. Training records retained. HR Director receives priority session within 5 days.

## Phase 2 — Days 31-60
Phase 2 — Core Governance Build (Days 31–60) NorthStar Financial Services — AI Governance Remediation Programme
These actions complete the core compliance programme for High Risk systems. Conformity assessments are gate conditions for continued production use.
Ref | Action | System | Owner | Start Date | Deadline | EU AI Act Basis | Success Criteria
NS-ACT-007 | Complete conformity assessment for CreditScore Pro per EU AI Act Article 43. Assess against Articles 9-15 requirements. Issue Declaration of Conformity. Register in EU AI database. | NS-AI-001 CreditScore Pro | Head of Credit Risk + Legal | 1 May 2026 | 30 May 2026 | Article 43 — Conformity Assessment ¦ Article 71 — Registration | Declaration of Conformity issued. EU AI database registration confirmed. AI Risk Committee approval obtained.
NS-ACT-008 | Complete conformity assessment for TalentMatch AI per EU AI Act Article 43. Note: bias audit results (NS-ACT-002) must be available before conformity assessment commences. | NS-AI-003 TalentMatch AI | HR Director + Legal | 1 May 2026 | 30 May 2026 | Article 43 — Conformity Assessment ¦ Article 71 — Registration | Declaration of Conformity issued. EU AI database registration confirmed. Dependency: NS-ACT-002 bias audit complete.
NS-ACT-009 | Implement technical documentation for CreditScore Pro per Article 11 and Annex IV. Document: system purpose, architecture, training data, performance metrics, known limitations, human oversight design. | NS-AI-001 CreditScore Pro | ML Engineering + Head of Credit Risk | 1 May 2026 | 15 May 2026 | Article 11 + Annex IV — Technical Documentation | Complete technical file produced. Reviewed by Legal. Retained in compliance document management system.
NS-ACT-010 | Implement technical documentation for TalentMatch AI per Article 11 and Annex IV. Require HireFlow Technologies to supply training data documentation, model architecture, and performance evidence. | NS-AI-003 TalentMatch AI | HR Director + Legal | 1 May 2026 | 15 May 2026 | Article 11 + Annex IV — Technical Documentation | Technical file complete including vendor-supplied documentation. HireFlow formally requested to provide required materials.
NS-ACT-011 | Implement model monitoring framework for CreditScore Pro. Define accuracy, fairness, and drift thresholds. Implement automated alerts for threshold breaches. Assign monitoring responsibility. | NS-AI-001 CreditScore Pro | ML Engineering + Head of Credit Risk | 1 May 2026 | 30 May 2026 | Article 9 — Risk Management ¦ Article 15 — Accuracy | Monitoring dashboard live. Thresholds documented and approved. Alert recipients defined. First monthly report produced.
NS-ACT-012 | Complete governance gate review for DocIntel Underwriting. Legal review of High Risk classification. Define production readiness criteria. Agree go/no-go process for production deployment. | NS-AI-006 DocIntel Underwriting | Head of Insurance + Legal + CRO | 1 May 2026 | 30 May 2026 | Article 6 — Classification ¦ Article 43 — Conformity (pre-production) | Legal opinion on classification received. Production readiness criteria documented. AI Risk Committee briefed on go/no-go process.
NS-ACT-013 | Update vendor contract with FraudTech GmbH to include EU AI Act compliance clauses covering: compliance representations, audit rights, model change notification, liability provisions. | NS-AI-002 FraudGuard 360 | Head of Payment Operations + Legal | 1 May 2026 | 30 May 2026 | Article 28 — Deployer Obligations | Updated contract clauses agreed with FraudTech GmbH. Legal sign-off obtained. Effective at next contract renewal.

## Phase 3 — Days 61-90
Phase 3 — Embedding and Normalisation (Days 61–90) NorthStar Financial Services — AI Governance Remediation Programme
These actions embed governance into NorthStar's operating rhythm and demonstrate regulatory compliance to the Board and external parties.
Ref | Action | System | Owner | Start Date | Deadline | EU AI Act Basis | Success Criteria
NS-ACT-014 | Produce first AI Portfolio Risk Report for Board Risk Committee. Cover: risk tier summary, maturity score movements, conformity assessment status, open remediation actions, incidents to date, Q3 governance plan. | All systems | Chief Risk Officer | 1 Jun 2026 | 30 Jun 2026 | NS-POL-AI-001 Section 7 — Board Reporting | Report produced and presented to Board Risk Committee. Board minutes confirm receipt and approval of governance programme progress.
NS-ACT-015 | Implement model monitoring framework for TalentMatch AI. Define fairness thresholds by demographic group. Implement automated shortlisting outcome tracking. Monthly override rate reporting. | NS-AI-003 TalentMatch AI | ML Engineering + HR Director | 1 Jun 2026 | 30 Jun 2026 | Article 9 — Risk Management ¦ Article 14 — Human Oversight | Monitoring framework live. Fairness thresholds documented. First monthly shortlisting outcome report produced.
NS-ACT-016 | Complete AI incident response procedure for all High Risk systems. Define incident classification, escalation paths, regulatory notification process, and post-incident review template. | NS-AI-001, NS-AI-003, NS-AI-006 | CRO + System Owners + Legal | 1 Jun 2026 | 15 Jun 2026 | NS-POL-AI-001 Section 9 — Incident Management | Incident response procedures documented for each High Risk system. Tabletop exercise conducted. Procedures approved by AI Risk Committee.
NS-ACT-017 | Commission HireFlow Technologies to supply complete training data documentation and independent bias audit results for TalentMatch AI model. Formal written request issued. | NS-AI-003 TalentMatch AI | HR Director + Legal | 1 Jun 2026 | 30 Jun 2026 | Article 28 — Deployer Obligations ¦ Article 10 — Data Governance | Formal request issued to HireFlow. Response received and reviewed by Legal. Escalation plan agreed if vendor non-responsive.
NS-ACT-018 | Conduct first annual AI governance review cycle. Confirm all system classifications remain accurate. Confirm all documentation is current. Identify any new AI systems deployed since April 2026. | All systems | Chief Risk Officer + AI Risk Committee | 15 Jun 2026 | 30 Jun 2026 | NS-OM-AI-001 Section 3.3 — Annual Cycle | Annual review report produced. AI System Inventory updated. Any new systems identified and registered. Q3 governance plan approved.

## Action Tracker
Master Action Tracker — All 18 Actions Across 3 Phases NorthStar Financial Services — AI Governance Remediation Programme
Update the STATUS column weekly. RAG status updates automatically based on deadline proximity.
Action Ref | Action Summary | System | Owner | Deadline | Priority | Status | Notes
NS-ACT-001 | Implement human override for TalentMatch AI shortlisting | TalentMatch AI | HR Director | 1 Apr 2026 | CRITICAL | In Progress
NS-ACT-002 | Commission TalentMatch AI bias audit | TalentMatch AI | HR Director + ML Eng | 30 Apr 2026 | CRITICAL | In Progress
NS-ACT-003 | Document CreditScore Pro SHAP explainability to Art. 13 standard | CreditScore Pro | Head of Credit Risk | 15 May 2026 | CRITICAL | Not Started
NS-ACT-004 | Implement SupportBot Aria mobile AI disclosure | SupportBot Aria | Head of Cx + DialogueTech | 30 Apr 2026 | MEDIUM | In Progress
NS-ACT-005 | Establish AI Risk Committee | All systems | Chief Risk Officer | 15 Apr 2026 | HIGH | In Progress
NS-ACT-006 | Deliver AI governance training to all system owners | All systems | Chief Risk Officer | 30 Apr 2026 | HIGH | Not Started
NS-ACT-007 | Complete CreditScore Pro conformity assessment + EU registration | CreditScore Pro | Head of Credit Risk + Legal | 30 May 2026 | CRITICAL | Not Started
NS-ACT-008 | Complete TalentMatch AI conformity assessment + EU registration | TalentMatch AI | HR Director + Legal | 30 May 2026 | CRITICAL | Not Started
NS-ACT-009 | Complete CreditScore Pro technical documentation (Art. 11) | CreditScore Pro | ML Engineering | 15 May 2026 | CRITICAL | Not Started
NS-ACT-010 | Complete TalentMatch AI technical documentation (Art. 11) | TalentMatch AI | HR Director + Legal | 15 May 2026 | CRITICAL | Not Started
NS-ACT-011 | Implement CreditScore Pro model monitoring framework | CreditScore Pro | ML Engineering | 30 May 2026 | HIGH | Not Started
NS-ACT-012 | Complete DocIntel Underwriting governance gate review | DocIntel Underwriting | Head of Insurance + Legal | 30 May 2026 | HIGH | Not Started
NS-ACT-013 | Update FraudGuard 360 vendor contract (EU AI Act clauses) | FraudGuard 360 | Head of Payments + Legal | 30 May 2026 | MEDIUM | Not Started
NS-ACT-014 | Produce first Board AI Portfolio Risk Report | All systems | Chief Risk Officer | 30 Jun 2026 | HIGH | Not Started
NS-ACT-015 | Implement TalentMatch AI monitoring framework | TalentMatch AI | ML Engineering + HR | 30 Jun 2026 | HIGH | Not Started
NS-ACT-016 | Complete AI incident response procedures (High Risk systems) | High Risk systems | CRO + System Owners | 15 Jun 2026 | MEDIUM | Not Started
NS-ACT-017 | Request HireFlow training data + bias audit documentation | TalentMatch AI | HR Director + Legal | 30 Jun 2026 | MEDIUM | Not Started
NS-ACT-018 | Conduct first annual AI governance review cycle | All systems | CRO + AI Risk Committee | 30 Jun 2026 | MEDIUM | Not Started